## StoryBook
Title | Description | Acceptance Criteria | Criticality | Release Num | Subtasks | Time Estimates (Hours) | Notes
A2 | As a cook, I need to view the orders coming in, so that I can cook food effiecently. | Interface includes list of orders in all of their details. Interface lists the orders based on when the order was submitted. | 5 | 0 3 | Design order view panel (displays current orders). | 4 | Pushed to release 3.
A3 | As an employee, I need log in to the system to prep a table, so that a customer can enter their order. | Interface should prompt user to log in on system startup only. Log in interface will prompt for user privileges. | 5 | 0 | Hardcode credentials for waitstaff login. Navigate to order form when waitstaff credentials entered. | 6
C1 | As a customer, I need a simple payment interface, so that I can pay for my meal. | Interface includes summary of order. Interface includes price of meal with tax added on. Interface includes ability to select a payment method. Interface allows for submitting of payment. | 5 | 0 | Design payment panel on user side. Create flag attribute for order to signal a completed payment. | 3 | Began in release 0, polished throughout project.
A1 | As a waiter, I need to view the orders coming in, so that I can run food to the customer quickly. | Interface includes order number and table number. Interface includes estimated wait time for order to be completed. | 5 | 1 3 | Fill list with current orders. Display order and table number next to orders. Approximate the wait time for each order. | 4 | Pushed to release 3 due to its similarity to cook order viewer.
A5 | As a manager, I need to add/edit descriptions for items on the menu, so I can inform my customers. | Manager is able to add a 1-4 sentence description of each food on the menu. Customer interface displays 1-4 sentence description of each food on the menu. | 4 | 1 | Create textbox to add description for a new menu item. Allow for changes to be made to each item description. | 10
C10 | As a customer, I need to view descriptions for items on the menu, so I can know what I am ordering. | Menu items have text based descriptions. Administrators have ability to modify descriptions. | 3 | 1 | Create a textbox to display the description. | 6
C5 | As a customer, I need to see my order in a cart, so that I can make changes prior to submitting my order. | Cart should have the ability to checkout. Cart should subtotal the order. Cart should show a modifiable list of the contents in the order. | 4 | 2 | Create required classes for an order and menu item. Display the order in the cart with add/remove funtionality. Show selected options in cart | 10
A4 | As a manager, I need to add/remove items from the menu so that I can keep with (un)popular ingredient trends. | Administrative privileges allow for item customization/modification. Admin interface includes add, edit, and remove buttons next to menu items. | 3 | 1 | Create add/remove functionality for menu items. Save changes to database. | 12 | implementation depth unclear, will be implemented in phases.
C13 | As customer, I need a digital reciept interface, so that I can see the final cost of my meal(the amount I was billed). | Receipt is viewable before feedback form. Receipt includes cost with tip and tax with meal calculation. Digital signature provides security for the payment. | 3 | 2 | Create a new form for the receipt. Display final cost with all options included. Add in tax with calculation. Provide a digital signature for each order. | 5
C7 | As a customer, I need to be able to give feedback based on experience, so that the restuarant can improve. | Feedback should be submitted via a form. A rating system should be in place for customers to select a rating. Comments regarding order are encouraged and user is prompted. Form includes the question, "Would you come again?" (Yes/No). | 4 | 2 | Create feedback UI. Attach feedback to an order. Allow for comments and a rating scale. | 4 | start in 0, finish in 1
C12 | As a customer, I need a clean and organized touch interface, so that I can avoid mistakes. | Interface follows usability standards. Food is organized in menu categories. Drinks are seperate from food. | 3 | 2 | Layer selection panels to avoid cluttered interface. Increased button size. Improve focus by reducing number of elements on screen. | 8
C9 | As a customer, I need to customize my food, so that I can have my meal prepared how I like it. | Food customization is defined by a prep based heirarchy system. Food is broken down for customization which allows for add-ons and other food items based on user preference and system restrictions defined by an administrator. | 5 | 2 | Link specific options to menu items. | 16 | important but takes time.
U1 | As a manager, I need a log to track orders, so that I can update finances and inventory according to the information in the logs. | Log is in the form of a file. Log file must store all food items contained in every order. Log file should seperate food items into categories and count the amounts of each. | 4 | 2 | Create a text file containing a list of menu items and how many of each were purchased. | 20 | persistant data
U2 | As a manager, I need all logs to be saved on the computer, so that I can view logs outside of the system. | Log contains order number and order information. Saved in a folder on system. | 5 | 2 | Standard output to text file (standard file writer). Format line by line for readability. | 2 | persistant data
A6 | As a cook, I need to view the current status of each order, so that I can prioritize what I am cooking. | List of tickets for each table is given. Cook can view how long each table has been waiting. | 3 | 3 | Create order status UI. Create current order list. Add flag attribute to each order indicating current state. Implement timecost attribute for orders. | 6 | dependent on ordering interface
A7 | As a cook, I need an interface that allows me to update the status of the order, so that the customer can track their order. | Cook is able to update the status of the order(not started, started, on the way). | 2 | 3 | Implement the changing of an order's status by a cook. Display order status on customer side. | 8
C11 | As a customer, I need to have meal deals visible to me, so that I can simplify my purchase decisions. | Main interface displays meal deals created by an administrator that customers can choose to bypass during the order selection process. | 2 | 3 | Add meal deals as a category to the menu. | 6
C2 | As a customer, I need to track the progress of my order, so I can approximate my wait time. | Should be displayed as a status. Status should include how far along the meal is in progress. | 2 | 3 | Display the total estimated wait time for the order. Display the current status of the order. | 8 | Dependent on chef interface
C3 | As a customer, I need an intuitive food selection interface, so that I can customize my meal. | Interface includes prep based heirarchy for selecting food. Interface should provide pictures of selected food items. Interface includes ability to remove items from selection. | 4 | 3 | Implement editing functionality for orders. Adjust price and time cost accordingly. | 6 | important but depends on manager side building out food items
C4 | As a customer, I need calories displayed next to food items, so that I can track my calorie intake. | Calories should be displayed next to the food item. | 2 | 3 | Implement calorie attribute for menu items. Display calorie values in customer UI. | 6
C6 | As a customer, I need to request a refill for my drink, so that I can add to my order. | A button on the main interface allows for user to request another drink/refill. | 2 | 3 | Add "refill" button to order form. Implement item checking to only allow refills for drinks. | 8 | simple but unimportant
C8 | As a customer, I need to be able to call the waiter over from the kiosk, so that I can request further service. | Main interface needs a button for requesting service. | 2 | 3 | Add a "call server" button to the customer UI. Display notice on admin side to send waiter to table X. | 2
C14 | As a customer, I need to be able to pick where I want to sit, so that I can be seated. | Customer can select from an open table. Table updates to indicate whether occupied or free. Waitor is notified if their table is updated. | 1 | N/A |  | 16 | Removed from system
U3 | As a manager, I need to view the current stock of all food items, so that I can maintain sufficient stock in the restaurant. | Each ingredient is totalled at the end of the day. Admin can view the inventory, the total number of remaining ingredients. Admins can add to the total ingridient quantity. Admins can subtract from inventory total. | 1 | N/A |  | 24 | Removed from system